## Sheet1
Risk | Impact | Likelihood | Mitigation Strategy | Responsible Individual
Data Privacy and Security Breaches | Very High (Legal liabilities, reputational damage, fines) | Medium | - Encrypt all sensitive data during transmission and storage. | Compliance Officer (Sarah Johnson)
|  |  | - Implement strict access controls (role-based access). | IT Support, Identity & Acess Management Control (Michael Turner)
- Ensure GDPR and local compliance.
- Conduct regular security audits and penetration tests.
Regulatory Changes (KYC, AML) | High (Non-compliance risks, legal and financial consequences) | Medium to High | - Regularly monitor regulatory changes. | Compliance Officer (Sarah Johnson)
|  |  | - Ensure the system is flexible enough for quick updates to compliance rules. | Business Analyst (Smita Nikalje)
- Agile development to implement changes rapidly.
- Regular testing to ensure ongoing compliance.
Integration Challenges of UiPath with Core Banking System (BMS) and Customer Management System (CMS) | High (Could delay or disrupt account creation and other key processes) | Medium | - Conduct system integration assessment in the initial phases. | Developer (Alan Richards)
|  |  | - Address integration issues early with IT support. | IT Support (Michael Turner)
UiPath document understsnding Accuracy and Document Quality | High (Potential errors or delays due to poor document quality) | Medium | - Implement document quality validation before processing. | Business Analyst (Smita Nikalje)
|  |  | - Flag low-quality documents for manual review. | Developer (Alan Richards)
|  |  | - Provide clear guidelines for users on acceptable document quality. | Business User
System Downtime or Availability Issues | High (Disruptions to the onboarding process) | Medium to Low | - Implement redundant systems and backup servers. | IT Support (Michael Turner)
- Use monitoring tools for real-time detection of system issues.
- Schedule regular maintenance during low-traffic hours and inform customers in advance.
Inaccurate Data Entry or Document Verification | Medium (Data discrepancies, onboarding delays) | Low to Medium | - Implement multiple validation rules at each step. | Developer (Alan Richards)
|  |  | - Conduct comprehensive testing of OCR extraction and data validation. | Quality Assurance (Maria Gonzalez)
|  |  | - Develop exception handling for manual verification of flagged data. | Developer (Alan Richards)
Customer Adoption and Experience | Medium (Impact on customer satisfaction and onboarding efficiency) | Medium | - Create an intuitive user interface with clear instructions. | Business Analyst (Smita Nikalje)
|  |  | - Offer customer support for troubleshooting. | Quality Assurance (Maria Gonzalez)
|  |  | - Implement a feedback loop for continuous improvement. | Key business users
Scalability Issues | Medium (Potential bottlenecks with increasing customer volume) | Low to Medium | - Design the system for scalability with cloud-based solutions. | IT Support (Michael Turner)
|  |  | - Perform load testing to identify performance issues. | Developer (Alan Richards)
|  |  | - Add resources as needed to accommodate growth. | Project Manager